Event Planning Checklist

This checklist is intended to help you build a timeline that is specific to your PTA’s upcoming Program event. Remember to include the following:

# At Least 6-8 Weeks Before Your Event

- Connect with school administrators and faculty to gather support and secure your event location.

- Engage different members of your school community (teachers, parents, students, staff, administrators) to gather feedback.

- Determine when your event will be held using input from the planning committee, keeping in mind families’ needs and schedules.

- Reserve your location. Make sure you plan for a central area to welcome families and serve refreshments.

- Plan for accessibility for family members with disabilities. Is your event location accessible to those with mobility challenges? Would any families benefit from sign-language interpreters or other accommodations?

- Share event details and information with your PTA members. Recruit your planning team.

- Create a list of needed supplies for the event and begin collecting them.

# 4 Weeks Before Your Event

- Start holding regular planning meetings with your team.

- Begin promoting your event!

- Assign volunteer roles and leads.

- Begin the process of translating event materials and arranging for interpreters for non-English speaking families, if needed.

- Consider whether transportation to the event is a barrier and discuss potential solutions (e.g., use a school bus or provide bus passes).

- Ask for donations for event giveaways, including an incentive for families to complete the event evaluation form.

- Develop a plan for photo/video collection including a media release form.

# 2 Weeks Before Your Event

- Solicit volunteers needed for specific roles on event day.

- Continue promoting the event. Consider posting signs in school, asking room parents, teachers, and school staff to send flyers home with kids and include in the daily announcements.

- Order food and drinks. Provide healthy snacks and a comfortable place for families to gather, eat and socialize.

- Begin to organize materials needed for the event.

- Review all program materials and prepare volunteers for their roles during the event.

# A Week Before Your Event

- Ask volunteers to make phone calls to invite targeted families and ensure that caregivers understand the importance of their active participation during the event.

- Finalize event logistics, including creating a detailed day-of-event schedule and assigning specific volunteers to critical roles. (See Event Day Checklist.)

- Continue promoting the event.

- Check-in with volunteers to make sure they understand their roles during the event.

- Make copies of event materials/handouts and any parent takeaways.

# Within 2 Weeks After Your Event

- Formally thank volunteers and school and community participants.

- Formally thank participants for attending and include the Program Evaluation link in the message.

- Compile evaluation data and share with National PTA.

- Hold a debriefing session with your planning committee to discuss what went well and what you would do differently next year.